## Tabelle1
Time Log | Software Projekt 2023/2024
|  |  |  | Name: | Cosmin Constantin Andronescu
|  |  |  | Student ID / Matrikelnummer: | 3140874
Project Week | Calendar Week | From | To | Hours | Activities
1 | 40 | 2023-10-02 | 2023-10-08 | 7 | Getting familiar with Scrum; Meeting with the team (7.10); Worked on the Vision document;
2 | 41 | 2023-10-09 | 2023-10-15 | 11 | Worked on the Vision document, chapters 3.2 and 5; Meeting with the team (11.10); Class meeting with the scrum team and professor (12.10); Meeting with the team (14.10);
3 | 42 | 2023-10-16 | 2023-10-22 | 11 | Worked on the Risk List; Meeting with the team (18.10); Finished the Risk List; Research OpenUP phases;
4 | 43 | 2023-10-23 | 2023-10-29 | 10 | Research Design Document; Meeting with the team (25.10); Class meeting with the scrum team and professor (26.10);
5 | 44 | 2023-10-30 | 2023-11-05 | 12 | Worked on Design Document; Meeting with the team (31.10); Class meeting with the scrum team and professor (2.11);
6 | 45 | 2023-11-06 | 2023-11-12 | 10 | Getting familiar with Qt; Designing Home Page Top Bar; Meeting with the team (8.11);
7 | 46 | 2023-11-13 | 2023-11-19 | 12 | Programming the Home Page Top Bar navigation; Meeting with the team (15.11); Class meeting with the scrum team and professor (16.11);
8 | 47 | 2023-11-20 | 2023-11-26 | 14 | Programming the Launch Screen, Designing the Admin Project Overview and Project Creation/Deletion Windows; Meeting with the team (22.11); Class meeting with the scrum team and professor (23.11);
9 | 48 | 2023-11-27 | 2023-12-03 | 11 | Fixes for Launch Screen; Designing and programming the Taskboard; Meeting with the team (29.11); Class meeting with the scrum team and professor (30.11);
10 | 49 | 2023-12-04 | 2023-12-10 | 12 | Designing and programming the Taskboard; Making the graphical User-Flow; Meeting with the team (6.11); Class meeting with the scrum team and professor (8.11);
11 | 50 | 2023-12-11 | 2023-12-17 | 15 | Designing and programming the Taskboard; Meeting with the team (13.12); Class meeting with the scrum team and professor (14.12);
12 | 51 | 2023-12-18 | 2023-12-24 | 10 | Designing and programming the Taskboard; Research on Layouts; Meeting with the team (20.12); Class meeting with the scrum team and professor (21.12);
13 | 52 | 2023-12-25 | 2023-12-31 | 10 | Designing and programming the Taskboard; Research on posters and logo design;
14 | 1 | 2024-01-01 | 2024-01-07 | 11 | Designing and programming the Taskboard; Research on posters and logo design; Meeting with the team (03.01);
15 | 2 | 2024-01-08 | 2024-01-14 | 17 | Designing the logo; Designing poster; Meeting with the team (10.01); Class meeting with the scrum team and professor (11.01);
16 | 3 | 2024-01-15 | 2024-01-21 | 22 | Finishing Taskboard; Meeting with the team (17.01); Class meeting with the scrum team and professor (18.01);
17 | 4 | 2024-01-22 | 2024-01-25 | 36 | Finishing Implementing Layouts; Working on other Windows UI; Finishing User-Flow; Completing my sections in Lessons Learned and User Manual;
Formulas:
Calendar Week = ISOWEEKNUM([From])
To = [From]+6
From = [From, row above]+7