## Risks
Scrummy 1.0 Risk List
Risk ID | Date Identified |  | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 16.10.2023 | Project deadline | Deadline for the finished product is not met | Direct | Medium | High | 9 |  | Compromise project specific phase timeline in order to meet final product deadline
2 | 16.10.2023 | Interface | User Interface not having the "User friendly" quality because of lack of design experience | Direct | High | Medium | 10 |  | Allocate enough resources(time, team members) for the interface development
3 | 17.10.2023 | Communication | Misscommunication due to the online work environment (No physical work office) | Direct | Medium | Medium | 5 |  | Transparency and meetings between development teams for an overview of the project
4 | 17.10.2023 | Requirements | Final product not meeting requirements | Direct | High | High | 20 |  | Implement robust quality assurance and testing processes to verify compliance with requirements at every phase of the project
5 | 18.10.2023 | Code Issues | Due to the lack of experience, the software is shipped with bugs | Direct | High | High | 20 |  | Allocate enough resources for the debugging process
6 | 18.10.2023 | Human Resources | A vital team member to the development leaves the project | Indirect | High | Low | 10 |  | Encouragement between team members
7 | 18.10.2023 | Poor Management | Development phases not being properly managed | Direct | High | Medium | 15 |  | Proper scheduling before the development phases start by taking in account the available resources
8 | 18.10.2023 | Productivity Issues | Productivity diminishing due to prioritization of other classes | Direct | Medium | Medium | 10 |  | Set project milestones and deadlines, along with regular progress reviews to allow students to allocate sufficient time for the project development and balance their commitments
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
Note on E2: Type = I (indirect) or D (direct)
Note on F2: Impact is a numerical value, usually between 1 and 5, that represents the impact to the project if the risk comes true. 5 is a HIGH IMPACT and 1 is LOW IMPACT.
Note on G2: Probability is the percentage chance that a risk will occur.
Note on H2: Magnitude is the result of the multiplication of Probability and Impact, providing a joint metric suitable for sorting.